## Summary
333 Toy Crawford Rd - 43x10 Elevated Sunroom Replacement: Demo, New Structure, Siding, Electrical, HVAC | [5 empty] | Project Totals
[6 empty] | Labor Cost | 16073.71
Project | 43x10 Elevated Sunroom Replace: New Posts/Beam/Floor/Walls, Vinyl Siding, 6 Windows, Mini-Split |  |  |  |  | Material Cost | 19716.087
Source Scope | 333_Toy_Crawford_Sunroom_Scope.txt |  |  |  |  | Equipment Cost | 1805
Template Anchor | Basement_Remodel_Breakdown_Locked_Template_v1.xlsx |  |  |  |  | Grand Total | 37594.797
Overall Footprint SF | 430 |  |  |  |  | Revenue: | 66200
Ceiling Height | 8
Note | Use this workbook as a locked template. Populate detail rows only; preserve formulas, tabs, and section order. |  |  |  |  | GP | 28605.203
[6 empty] | GP % | 43.21%
Section | Labor Cost | Material Cost | Equipment Cost | Section Total | Labor Hours
General Conditions, Temporary Shoring & Structural Support | 1373.96 | 1140 | 0 | 2513.96 | 36
Selective Demo - 43x10 Elevated Sunroom to Bearing Points (3 Dump Runs) | 1670 | 1470 | 1350 | 4490 | 48
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | 1524.1 | 2406.16 | 95 | 4025.26 | 44
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | 2994.05 | 3917.7 | 360 | 7271.75 | 87
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | 2382.95 | 2475.75 | 0 | 4858.7 | 69
Windows (6 x 36x60) & Exterior Pre-Hung Door (36x80) | 665.25 | 2450 | 0 | 3115.25 | 19
Roof Integration - Reattach Shed Roof, Flashing & 2 Patch/Repairs | 845.1 | 407 | 0 | 1252.1 | 24
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | 1560 | 1701.425 | 0 | 3261.425 | 40
HVAC - Ductless Mini-Split $2,500 Allowance | 390 | 2645 | 0 | 3035 | 10
Insulation - Exterior Wall Cavities (504 SF) & Floor Cavity (430 SF) | 237.65 | 356.552 | 0 | 594.202 | 7
Drywall - Walls Only 848 SF, Level 3 Finish | 2226.95 | 701.5 | 0 | 2928.45 | 65
Cleanup & Project Closeout | 203.7 | 45 | 0 | 248.7 | 6
Not Applicable | 0 | 0 | 0 | 0 | 0
Not Applicable | 0 | 0 | 0 | 0 | 0
Not Applicable | 0 | 0 | 0 | 0 | 0
Not Applicable | 0 | 0 | 0 | 0 | 0
TOTALS | 16073.71 | 19716.087 | 1805 | 37594.797 | 455

## Labor_Detail
Section | Trade Role | Hours | Rate | Labor Cost | Notes | Rate Category
General Conditions, Temporary Shoring & Structural Support | Project Manager | 8 | 47.87 | 382.96 | Coordinate all work per IRC 2018 and NEC; verify existing electrical disconnect condition prior to reuse and modification; install jobsite protection at access points and adjacent finishes below work area; coordinate temporary shoring plan before any demolition begins; NOTE: all work sequence governed by shoring plan - shoring must be in place before any structural demolition | Project Manager
General Conditions, Temporary Shoring & Structural Support | Team Lead | 8 | 39 | 312 | Install temporary shoring and structural support system to maintain existing shed roof during full demolition and reconstruction phases; shoring must be designed for 43-ft roof span and remain until new wall structure is fully framed, sheathed, and capable of carrying roof loads; install all jobsite protection along access paths and adjacent finished areas below | Team Lead
General Conditions, Temporary Shoring & Structural Support | General Labor | 20 | 33.95 | 679 | Erect temporary shoring system - 43-ft roof span: install vertical shores, horizontal wales, and bracing as required; maintain and inspect shoring daily throughout demolition and rebuild; remove and dispose of shoring materials at project completion after roof is permanently secured | General Labor
Selective Demo - 43x10 Elevated Sunroom to Bearing Points (3 Dump Runs) | Team Lead | 8 | 39 | 312 | Demo planning: confirm all bearing points before any cutting; coordinate demo sequence around active shoring; plan debris lowering method from elevated structure; 3 dump trailer runs budgeted per scope | Team Lead
Selective Demo - 43x10 Elevated Sunroom to Bearing Points (3 Dump Runs) | General Labor | 40 | 33.95 | 1358 | Demolish existing 43x10 elevated sunroom down to bearing points required for new construction: remove existing 6x6 posts, floor framing, subfloor, wall framing, windows, and ceiling assemblies; remove all existing substandard structural components; preserve existing shed roof system with temporary shoring throughout; lower all demo debris from elevated structure to ground; 3 dump trailer runs for all demolition debris | General Labor
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | Team Lead | 6 | 39 | 234 | Foundation coordination: confirm footer locations near existing pad; confirm post spacing for new primary beam and floor system loads; confirm post bracket alignment before concrete sets; plan 3-ply 2x12 beam construction and erection sequence | Team Lead
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | General Labor | 12 | 33.95 | 407.4 | Cut and install concrete footers at each of 8 post locations near existing pad - 12"x12"x12" each (8 CF total); hand-mix bags practical for this footer size; allow cure before loading post brackets | General Labor
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | General Labor | 4 | 33.95 | 135.8 | Install galvanized post brackets anchored to each footer after cure - 8 post bases; confirm alignment and elevation before proceeding to posts | General Labor
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | General Labor | 12 | 33.95 | 407.4 | Install 8 new 6x6 pressure-treated posts on post brackets - 8 posts x 1.5 hrs each = 12 hrs; plumb, brace, and confirm height at each post before beam installation | General Labor
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | General Labor | 10 | 33.95 | 339.5 | Build and install (1) primary beam approximately 44 LF consisting of 3-ply 2x12 dimensional lumber fastened per code; assemble plies, nail/bolt per IRC, set on post tops; all framing per IRC span tables and loading requirements | General Labor
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | Team Lead | 8 | 39 | 312 | Floor system coordination: confirm PT joist sizing per IRC for 10-ft span; plan vinyl soffit installation sequence beneath floor framing before joists are set; confirm subfloor adhesive and fastening requirements | Team Lead
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | General Labor | 40 | 33.95 | 1358 | Frame new floor system using PT framing lumber per IRC span requirements - 34 joists at 16" OC spanning 10 ft (43-ft length); install ledger boards, rim joists, blocking, and hangers; all framing elevated - allow additional time for staging and elevated work | General Labor
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | General Labor | 9 | 33.95 | 305.55 | Install subfloor sheathing glued and fastened per IRC - 15 sheets 3/4" T&G at 0.60 hr/sheet | General Labor
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | General Labor | 5 | 33.95 | 169.75 | Install insulation in floor cavity - 430 SF; batt insulation sized per cavity depth between PT joists | General Labor
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | General Labor | 25 | 33.95 | 848.75 | Install vinyl soffit system beneath floor framing - 5 squares (430 SF); installed from below, overhead work throughout; protects floor cavity from weather and pest intrusion; include all J-channel, F-channel, vents, and accessories | General Labor
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | Team Lead | 8 | 39 | 312 | Wall framing and siding coordination: confirm window and door rough opening locations; confirm vinyl siding profile and color before ordering; plan siding sequence around 6 window and 1 door openings | Team Lead
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | General Labor | 28 | 33.95 | 950.6 | Frame exterior walls using 2x4 lumber at 16" OC - 63 LF (3 exposed sides: 43-ft front + 2x 10-ft ends) at 0.45 hr/LF; frame window rough openings for 6 windows; frame door rough opening for 36x80 exterior door; install all headers, blocking, and required structural connections | General Labor
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | General Labor | 6 | 33.95 | 203.7 | Install exterior wall sheathing - 18 sheets OSB 7/16" at 0.40 hr/sheet; install weather-resistant barrier over full sheathed area; tape all WRB seams and integrate at window and door openings | General Labor
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | General Labor | 3 | 33.95 | 101.85 | Install WRB house wrap; tape seams; integrate at all openings | General Labor
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | General Labor | 18 | 33.95 | 611.1 | Install vinyl lap siding on all exterior wall surfaces - 5 squares; $150/square retail allowance; install starter strip, J-channel at all window and door perimeters, corner posts, and all trim accessories | General Labor
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | General Labor | 6 | 33.95 | 203.7 | Install all exterior trim at corners, window perimeters, door opening, and all siding transitions; caulk all joints and penetrations | General Labor
Windows (6 x 36x60) & Exterior Pre-Hung Door (36x80) | Team Lead | 4 | 39 | 156 | Window and door coordination: confirm vinyl window selection ($300 each allowance); confirm exterior door selection ($500 allowance) and hardware; confirm all 6 window and 1 door rough opening dimensions before ordering | Team Lead
Windows (6 x 36x60) & Exterior Pre-Hung Door (36x80) | General Labor | 12 | 33.95 | 407.4 | Install up to 6 new vinyl windows 36"x60" ($300 each retail allowance) - 6 x 2.0 hrs each; install plumb, level, shim, foam, flash per manufacturer; install sill pans, flashing tape, exterior caulk at all windows; install screens where included with window package | General Labor
Windows (6 x 36x60) & Exterior Pre-Hung Door (36x80) | General Labor | 3 | 33.95 | 101.85 | Install 1 exterior pre-hung door 36"x80" ($500 allowance) with hardware; set, shim, level, flash, foam, caulk; install lockset and weatherstripping; test operation | General Labor
Roof Integration - Reattach Shed Roof, Flashing & 2 Patch/Repairs | Team Lead | 6 | 39 | 234 | Roof integration coordination: plan roof reseating sequence while shoring is active; confirm flashing tie-in detail at wall-to-roof connection; plan 2 roof patch/repairs at previous vent locations; NOTE: shoring may be removed only after roof is permanently seated and secured on new walls | Team Lead
Roof Integration - Reattach Shed Roof, Flashing & 2 Patch/Repairs | General Labor | 18 | 33.95 | 611.1 | Reintegrate existing shed roof system onto new wall structure; install required flashing and tie-ins at roof-to-wall connection to maintain fully weather-tight condition; install flashing at all transitions and edges; complete up to 2 roof patch/repairs from previous venting locations; all work done with shoring active until roof is permanently secured; remove shoring only after roof is bearing on new wall structure and fully flashed | General Labor
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Team Lead | 4 | 39 | 156 | Electrical layout: assess existing disconnect condition before modification; plan breaker configuration for subpanel function; plan outlet layout per NEC spacing for 43x10 space; confirm 6 flush-mount and 2 fan locations before rough-in | Team Lead
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Electrical/HVAC | 30 | 39 | 1170 | Modify existing disconnect panel by replacing fuses with breaker configuration to function as subpanel - verify condition of existing panel before modification; install electrical rough-in per NEC requirements: outlets per IRC/NEC spacing throughout 43x10 space (est 10 outlets); wiring and boxes for 6 flush-mount light fixtures ($75 each allowance); wiring and structural support for 2 ceiling fans ($150 each allowance); install all switching and circuits as required; HVAC disconnect for mini-split | Electrical/HVAC
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Electrical/HVAC | 6 | 39 | 234 | Electrical finish: install 6 flush-mount light fixtures, 2 ceiling fans; install all outlet devices, switches, cover plates; test all circuits and devices | Electrical/HVAC
HVAC - Ductless Mini-Split $2,500 Allowance | Electrical/HVAC | 10 | 39 | 390 | Install 1 ductless mini-split system sized for 43x10 space ($2,500 allowance); includes indoor head unit, outdoor condenser, refrigerant line set, condensate drain routing, exterior wall penetration, mounting bracket/pad, thermostat/remote setup, startup and testing; standard line-set routing assumed | Electrical/HVAC
Insulation - Exterior Wall Cavities (504 SF) & Floor Cavity (430 SF) | General Labor | 7 | 33.95 | 237.65 | Install batt insulation in all exterior wall cavities - 504 SF (63 LF x 8 ft) at 0.012 hr/SF; floor insulation already installed in S14; seal accessible penetrations at framing | General Labor
Drywall - Walls Only 848 SF, Level 3 Finish | Team Lead | 4 | 39 | 156 | Drywall layout: walls only per scope (no ceiling drywall); Level 3 finish throughout; confirm all access panel locations before drywalling; NOTE: scope specifies walls only - ceiling finish not included | Team Lead
Drywall - Walls Only 848 SF, Level 3 Finish | General Labor | 18 | 33.95 | 611.1 | Install drywall on walls throughout sunroom - 30 sheets at 0.60 hr/sheet; 848 SF total: interior faces of 3 exterior walls (63 LF x 8 ft = 504 SF) + house-side wall (43 LF x 8 ft = 344 SF); NOTE: ceiling drywall not included per scope | General Labor
Drywall - Walls Only 848 SF, Level 3 Finish | General Labor | 43 | 33.95 | 1459.85 | Apply tape and 3 coats drywall compound - 848 SF; sand Level 3 finish throughout; install corner bead at all outside corners; ready for primer and paint | General Labor
Cleanup & Project Closeout | General Labor | 6 | 33.95 | 203.7 | Perform jobsite cleanup throughout and at completion; remove all construction debris from site; punch list walkthrough with customer | General Labor
Not Applicable | General Labor | 0 | 33.95 | 0 | Not Applicable | General Labor
Not Applicable | General Labor | 0 | 33.95 | 0 | Not Applicable | General Labor
Not Applicable | General Labor | 0 | 33.95 | 0 | Not Applicable | General Labor
Not Applicable | General Labor | 0 | 33.95 | 0 | Not Applicable | General Labor

## Material_Detail
Section | Material | Description | Quantity | Unit | Unit Cost | Waste Factor | Line Total | Notes
General Conditions, Temporary Shoring & Structural Support | Project Consumables | Caulk, fasteners, misc hardware | 1 | lot | 280 | 0% | 280
General Conditions, Temporary Shoring & Structural Support | Temporary Shoring Materials | Vertical shores, horizontal wales, bracing for 43-ft roof span | 1 | lot | 680 | 0% | 680 | Critical: must be designed for full roof load during demo and rebuild
General Conditions, Temporary Shoring & Structural Support | Jobsite Protection Materials | Plywood, tarps, barriers at access and adjacent finishes below | 1 | lot | 180 | 0% | 180
Selective Demo - 43x10 Elevated Sunroom to Bearing Points (3 Dump Runs) | Demo Supplies | Reciprocating blades, pry bars, demo bags, safety equipment | 1 | lot | 120 | 0% | 120
Selective Demo - 43x10 Elevated Sunroom to Bearing Points (3 Dump Runs) | Debris Disposal | 3 dump trailer runs per scope | 3 | ea | 450 | 0% | 1350 | Per scope
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | Concrete - Footers | 8 footers at 12x12x12; hand-mix bags; 16 x 80-lb bags | 16 | bag | 7.5 | 5% | 126 | Small footers - hand-mix more practical than ready-mix
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | Galvanized Post Brackets | 8 post bases - galvanized | 8 | ea | 32 | 0% | 256
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | Anchor Hardware for Post Brackets | Epoxy anchors or anchor bolts at each footer | 8 | set | 14 | 0% | 112
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | 6x6 PT Posts | 8 posts at approximately 10 ft | 8 | ea | 85 | 5% | 714
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | 2x12 Dimensional Lumber - Primary Beam | 132 LF of 2x12 for 3-ply x 44 LF beam | 132 | lf | 5.8 | 10% | 842.16
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | Beam Connection Hardware | Through-bolts, structural screws, bearing plates for 3-ply beam | 1 | lot | 180 | 0% | 180
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | Post Caps + Structural Hardware | Post-to-beam connectors and structural ties | 8 | ea | 22 | 0% | 176
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | PT Floor Joists | 34 joists spanning 10 ft - sized per IRC span | 34 | ea | 42 | 5% | 1499.4
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | PT Rim Joists and Ledger | Perimeter framing: 2x{D}+2x{W} = ~106 LF | 1 | lot | 380 | 10% | 418
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | Joist Hangers | At all joist-to-ledger and joist-to-beam connections | 34 | ea | 2.8 | 5% | 99.96
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | Subfloor Sheathing 3/4 in T&G | 15 sheets glued and fastened | 15 | sheet | 62 | 5% | 976.5
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | Subfloor Adhesive | PL400 construction adhesive | 4 | ea | 8 | 0% | 32
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | Floor Batt Insulation | 430 SF in floor cavity | 430 | sf | 0.58 | 10% | 274.34
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | Vinyl Soffit - Below Floor | 5 squares under floor framing | 5 | sq | 95 | 10% | 522.5 | Weather and pest protection below floor structure
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | Soffit Accessories | J-channel, F-channel, vents, fasteners for floor soffit | 1 | lot | 95 | 0% | 95
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | 2x4 Wall Studs | 52 studs for 63 LF walls | 52 | ea | 6.5 | 10% | 371.8
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | 2x4 Wall Plates | 24 pcs - 63 LF x 3 | 24 | ea | 6.5 | 10% | 171.6
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | Window Headers and Blocking | LVL or built-up headers at 6 window openings | 1 | lot | 180 | 10% | 198
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | Door Header and Blocking | Header at 36-in door opening | 1 | ea | 55 | 5% | 57.75
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | Wall Sheathing 7/16 in OSB | 18 sheets exterior walls | 18 | sheet | 22 | 10% | 435.6
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | House Wrap WRB | Weather-resistant barrier full wall area | 1 | lot | 95 | 0% | 95
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | WRB Tape and Accessories | Seam tape, window integration tape | 1 | lot | 45 | 0% | 45
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | Vinyl Lap Siding (allowance) | 5 squares at $150/sq retail | 5 | sq | 150 | 10% | 825 | Allowance per scope
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | Siding Accessories | Starter strip, J-channel, corner posts, utility trim | 1 | lot | 120 | 0% | 120
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | Exterior Trim | Corner boards, window and door surround trim | 1 | lot | 120 | 10% | 132
Wall Framing - 63 LF Exterior, Sheathing, WRB & Vinyl Siding | Exterior Caulk | All siding transitions and penetrations | 3 | ea | 8 | 0% | 24
Windows (6 x 36x60) & Exterior Pre-Hung Door (36x80) | Vinyl Windows 36x60 (allowance) | 6 at $300 each retail | 6 | ea | 300 | 0% | 1800 | Allowance per scope
Windows (6 x 36x60) & Exterior Pre-Hung Door (36x80) | Exterior Door 36x80 (allowance) | $500 retail with hardware | 1 | ea | 500 | 0% | 500 | Allowance per scope
Windows (6 x 36x60) & Exterior Pre-Hung Door (36x80) | Window Install Materials | Flashing tape, foam, sill pan, exterior caulk at 6 windows | 1 | lot | 95 | 0% | 95
Windows (6 x 36x60) & Exterior Pre-Hung Door (36x80) | Door Install Materials | Flashing tape, foam, threshold, sill pan | 1 | lot | 55 | 0% | 55
Roof Integration - Reattach Shed Roof, Flashing & 2 Patch/Repairs | Roof-to-Wall Flashing | Step flashing, counter flashing, and cap flashing at roof tie-in | 1 | lot | 220 | 10% | 242
Roof Integration - Reattach Shed Roof, Flashing & 2 Patch/Repairs | Roof Patch Materials | Shingles and materials for 2 patch/repairs at old vent locations | 1 | lot | 120 | 0% | 120 | Match existing shingle as closely as possible
Roof Integration - Reattach Shed Roof, Flashing & 2 Patch/Repairs | Roofing Sealant | Lap cement, silicone at all flashing transitions | 1 | lot | 45 | 0% | 45
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Electrical Panel Conversion Kit | Breaker kit to convert existing fuse disconnect to breaker subpanel | 1 | lot | 180 | 0% | 180
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Breakers | Breaker set for converted panel | 1 | lot | 95 | 0% | 95
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Wire 14/2 NM | 15A lighting and outlet circuits throughout | 600 | lf | 0.38 | 10% | 250.8
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Wire 12/2 NM | 20A dedicated circuits | 200 | lf | 0.55 | 10% | 121
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Electrical Boxes | Outlet, switch, fan, fixture boxes | 25 | ea | 1.5 | 5% | 39.375
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Outlet Devices | NEC-spaced outlets throughout 43x10 space | 10 | ea | 4.5 | 5% | 47.25
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Switches | Lighting and fan switching | 4 | ea | 6 | 5% | 25.2
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Flush-Mount Fixtures (allowance) | 6 at $75 each | 6 | ea | 75 | 0% | 450 | Allowance per scope
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Ceiling Fans (allowance) | 2 at $150 each | 2 | ea | 150 | 0% | 300 | Allowance per scope
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Cover Plates | Decorator style throughout | 1 | lot | 35 | 0% | 35
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | GFCI Outlets | NEC required locations | 2 | ea | 18 | 5% | 37.8
Electrical - Disconnect to Subpanel, Outlets, 6 Fixtures, 2 Fans & Switches | Electrical Misc | Connectors, staples, wire nuts, tape | 1 | lot | 120 | 0% | 120
HVAC - Ductless Mini-Split $2,500 Allowance | Mini-Split System (allowance) | 1-zone system sized for 430 SF - $2,500 retail | 1 | lot | 2500 | 0% | 2500 | Allowance per scope; confirm BTU sizing for 430 SF space
HVAC - Ductless Mini-Split $2,500 Allowance | Condensate Drain Materials | PVC drain from indoor head to discharge | 1 | lot | 45 | 0% | 45
HVAC - Ductless Mini-Split $2,500 Allowance | Line Set Cover | PVC line hide at exterior | 1 | lot | 45 | 0% | 45
HVAC - Ductless Mini-Split $2,500 Allowance | Condenser Mounting | Pad or wall bracket at condenser | 1 | ea | 55 | 0% | 55
Insulation - Exterior Wall Cavities (504 SF) & Floor Cavity (430 SF) | R-13 Batt Insulation - Wall Cavities | 504 SF exterior wall cavities | 504 | sf | 0.58 | 10% | 321.552
Insulation - Exterior Wall Cavities (504 SF) & Floor Cavity (430 SF) | Air Seal Foam | Penetrations and plate lines | 1 | lot | 35 | 0% | 35
Drywall - Walls Only 848 SF, Level 3 Finish | Drywall 1/2 in - Walls | 30 sheets walls only | 30 | sheet | 14.5 | 10% | 478.5
Drywall - Walls Only 848 SF, Level 3 Finish | Joint Compound | 5-gal - 3-coat Level 3 | 4 | ea | 22 | 0% | 88
Drywall - Walls Only 848 SF, Level 3 Finish | Drywall Tape | Paper tape | 6 | roll | 6 | 0% | 36
Drywall - Walls Only 848 SF, Level 3 Finish | Corner Bead | Metal - all outside corners | 1 | lot | 35 | 0% | 35
Drywall - Walls Only 848 SF, Level 3 Finish | Drywall Screws | 1-5/8 in coarse thread | 4 | box | 16 | 0% | 64
Cleanup & Project Closeout | Final Clean Supplies | Broom, bags, blower | 1 | lot | 45 | 0% | 45
Not Applicable | Not Applicable | Not Applicable | 1 | lot | 0 | 0% | 0
Not Applicable | Not Applicable | Not Applicable | 1 | lot | 0 | 0% | 0
Not Applicable | Not Applicable | Not Applicable | 1 | lot | 0 | 0% | 0
Not Applicable | Not Applicable | Not Applicable | 1 | lot | 0 | 0% | 0

## Equipment_Detail
Section | Equipment or Misc Item | Quantity | Unit | Unit Cost | Line Total | Notes
Selective Demo - 43x10 Elevated Sunroom to Bearing Points (3 Dump Runs) | Dumpster - 3 Runs | 3 | ea | 450 | 1350 | 3 runs per scope
Foundation - 8 Post Footers, Post Brackets & 3-Ply 2x12 Primary Beam 44 LF | Concrete Mixer - Footers | 1 | day | 95 | 95 | Hand-mix footers on-site
Floor System - PT Framing, Subfloor, Floor Insulation & Vinyl Soffit Below | Scaffolding - Elevated Floor Work | 2 | day | 180 | 360 | Elevated floor framing and soffit install

## PM_Notes
Section | Risk Type | Issue | PM Recommendation
CRITICAL - Temporary Shoring Must Be In Place Before Any Demo | Safety/Structural | The existing shed roof must be continuously supported by a temporary shoring system before any structural demolition begins. This is the highest risk item on this project. The shoring system must be designed to carry the full roof load at a 43-ft span. Shoring must remain active until the new wall structure is fully framed, sheathed, and the roof is permanently reseated and flashed. | Design shoring plan before mobilizing. Install all shoring before touching any existing structural component. Inspect shoring daily. Do not remove shoring until TL confirms new walls are fully capable of carrying roof load. Roof integration and final flashing must be complete before shoring is removed.
Existing Disconnect Panel Condition - Verify Before Modification | Electrical Risk | Scope requires modifying the existing disconnect panel by replacing fuses with breakers to function as a subpanel. The condition of the existing panel must be verified before any modification. If the panel is deteriorated, unsafe, or not suitable for conversion, a new subpanel may be required at additional cost. | Electrician must assess existing disconnect panel condition before ordering breaker conversion kit. If panel enclosure, bus, or wiring is unsuitable, present replacement cost to customer. Verify existing panel can legally serve as subpanel in this jurisdiction.
Substandard Original Construction - Unknown Hidden Conditions | Production Risk | This project is replacing a structure that had improper original construction. Additional hidden structural deficiencies, non-code conditions, or connection issues may be discovered during demolition that are not visible before work begins. | Document all conditions discovered during demolition with photos. Stop and present any discovered structural issues to customer before proceeding. Any required correction of conditions outside the written scope = change order.
Roof Reintegration - Weather Exposure During Construction | Production Risk | Reintegrating the existing shed roof onto new walls creates a period of weather exposure. The transition from demolition to new wall framing to roof reseating must be coordinated with favorable weather. Emergency tarping must be on-site throughout the project. | Monitor weather forecast continuously during the demo and rebuild phase. Have tarps and fasteners staged on-site before demo begins. Plan roof reseating work to be completed in one continuous work session when possible. Do not leave roof open overnight without temporary weather protection.
Vinyl Soffit Under Floor - Overhead Work | Production Risk | 430 SF of vinyl soffit installed below the elevated floor framing is significant overhead work. This requires scaffolding or staging below the structure and is more labor-intensive than standard soffit work. | Confirm scaffolding is staged below floor before floor framing begins. Plan soffit installation immediately after floor framing and before subfloor is installed if access from above is possible. If installed from below, rolling scaffold is required.

## Assumptions
Category
Project name | 333 Toy Crawford Rd - 43x10 Elevated Sunroom Replacement |  | From scope / intake | Metadata
Overall footprint | 430 | SF | From intake and scope | Drives flooring, ceiling, production
Ceiling height | 8 | ft | From intake and scope | Drives wall area
Interior wall length | 8 | LF | From intake/drawings or assumptions | Drives framing and two-sided finishes
Structure | 43x10 = 430 SF elevated second-story sunroom replacement | SF | Full demo + rebuild | Drives framing, insulation, one-sided finishes | Existing shed roof preserved throughout via shoring
Shoring | 43-ft roof span temporary support |  | Must be in place before any demo | Drives drywall, paint | Critical: do not demo without shoring
Foundation | 8 x 6x6 PT posts on 12x12x12 footers | ea | Post brackets after footer cure | Drives trim | Small footers - hand-mix bags
Primary Beam | 3-ply 2x12 x 44 LF = 132 LF of 2x12 | LF | Per IRC span tables | Drives trim and CO logic
Floor | 34 PT joists 10-ft span; 15 sh subfloor; 430 SF insulation | SF | PT framing throughout | Scope alignment | 430 SF vinyl soffit below floor (5 squares)
Walls | 63 LF ext walls (3 sides); sheathing + WRB + vinyl siding | LF | House side = roof integration only | Scope alignment | 5 squares vinyl siding at $150/sq allowance
Windows | 6 x 36x60 vinyl at $300 each + 1 door at $500 | ea | All allowances per scope | Scope alignment | Confirm availability before ordering
Electrical | Fuse-to-breaker panel conversion + outlets + 6 fixtures + 2 fans | lot | NEC compliant | Drives tile materials and labor | Verify existing panel condition first
HVAC | 1-zone mini-split $2,500 allowance | ea | 430 SF space | Labor realism | Confirm BTU sizing
Drywall | 848 SF walls only - no ceiling drywall per scope | SF | Level 3 finish | Audit trail | Ceiling drywall not in scope
Insulation | 504 SF wall cavities + 430 SF floor = 934 SF total | SF | R-13 batt throughout
Total Labor Hrs | ~455 | hrs | All sections combined |  | See Labor_Detail for breakdown
Sell Price | $66,700 per previous scope |  |  |  | Cost basis shown in workbook

## Labor_Rates
Editable Labor Rates
Rate Category | Hourly Rate | Used For | Note
General Labor | 33.95 | Laborer, Carpenter, Painter, Drywall, Flooring, Tile, Cabinet install, countertop/template support | Edit B3 only
Team Lead | 39 | Any row marked Team Lead | Edit B4 only
Electrical/HVAC | 39 | Electrician, HVAC Tech, HVAC Helper | Edit B5 only
Plumbing | 33.92 | Plumber | Edit B6 only
Project Manager | 47.87 | Project Manager rows | Edit B7 only
Instructions | Change any rate in column B and all linked labor rows plus summary labor totals will update.
Example | Set General Labor to 42 to update all General Labor rows everywhere in the workbook.

## Template_Guide
Locked Template Guide
Purpose | Use this exact workbook as the anchor template for every basement remodel output.
How to use | 1) Upload this template 2) Upload PM intake/validation workbook 3) Upload scope PDF 4) Upload locked prompt 5) Ask AI to populate THIS workbook only.
Hard rules | Do not rename tabs, do not change summary layout, do not hardcode totals, do not remove labor rate controls.
Auto-create sections | AI must map scope items into the standard sections listed on Section_Master. Unused sections stay in Summary with zero totals; detail tabs only get rows for relevant sections.
Dropdowns | Detail tabs use dropdown lists for Section, Rate Category, Risk Type, and common Units to keep data normalized.
Change order logic | Use PM intake scope-alignment flags to note credit opportunities and change-order risks in PM_Notes.
Best practice | Always upload this template with the prompt so the AI can match structure, formulas, and layout instead of improvising.

## Data_Lists
Sections | Rate Categories | Risk Types | Units | Include?
General Conditions & Project Management | General Labor | Scope Gap | ea | Yes
Selective Demolition | Team Lead | Change Order Risk | lf | No
Framing | Electrical/HVAC | Credit Opportunity | sf
Windows & Exterior Openings | Plumbing | Existing Conditions | sheet
Plumbing & Waste Pump System | Project Manager | Takeoff Assumption | lot
Electrical |  | Structural Risk | gal
HVAC - 3 Zone Mini Split |  | Coordination | bag
Insulation & Air Sealing |  | Sequencing | box
Drywall & Finishing |  | Production Risk | roll
Suspended Ceiling System |  | Allowance Risk | set
Interior Doors, Trim & Hardware |  |  | pair
Flooring |  |  | day
Painting
Master Bathroom
Kitchen
Cleanup & Closeout

## Section_Master
Standard Section | Default Include | Use For / Notes
General Conditions & Project Management | Yes | Site setup, PM time, scheduling, protection
Selective Demolition | Yes | Selective demo, removals, disposal, concrete sawcut
Framing | Yes | Exterior/interior walls, soffits, chases, blocking
Windows & Exterior Openings | Yes | New windows, exterior doors, lintels, flashing
Plumbing & Waste Pump System | Yes | Bath, kitchen, laundry, below-slab, ejector/pump
Electrical | Yes | Subpanel, branch circuits, lighting, devices
HVAC - 3 Zone Mini Split | Yes | Mini split or other HVAC equipment and startup
Insulation & Air Sealing | Yes | Batt, foam, air sealing, sound attenuation
Drywall & Finishing | Yes | Wall board, taping, mud, sanding, access panels
Suspended Ceiling System | Yes | Drop ceiling grid, tile, access coordination
Interior Doors, Trim & Hardware | Yes | Interior doors, base, casing, hardware, trim
Flooring | Yes | LVP, tile underlayment, transitions, prep
Painting | Yes | Primer, finish paint, trim/door coating
Master Bathroom | Yes | Shower, tile, vanity, toilet, bath finishes
Kitchen | Yes | Cabinets, counters, sink/faucet, appliance set
Cleanup & Closeout | Yes | Final clean, punch support, closeout